## Blad1
Action Item List | [5 empty] | Status
Doc ID: | [5 empty] | O | Open
Date: | 2018-06-01 |  |  |  |  | C | Closed
[6 empty] | H | Hold
[6 empty] | IP | In progress
[6 empty] | Ob | Obsolete
Open action item list
ID | Initialization date | Due date | Description | Accountability |  | Status | Inform | Remarks
|  |  |  | Person(s) | Group
A001 | 2018-05-31 | 2018-06-13 | Look for a platform to organize all information concerning the community, (both education and companies), Github? | Witek ten Hove |  | C
A002 | 2018-05-31 | 2018-06-13 | Give a suggestion on how to organize this information based on stakeholder analysis | Witek ten Hove |  | IP
A003 | 2018-05-31 | 2018-06-01 | Plan bi-weekly kernteam progressmeetings | Carolien Stroomer |  | C
A004 | 2018-05-31 | 2018-06-01 | Make actionlist based on progressmeting 31-052-18 | Carolien Stroomer |  | C
A005 | 2018-05-31 | 2018-06-01 | Compile a draft version of an e-mail we are going to send to companies | Carolien Stroomer |  | C
A006 | 2018-05-31 | 2018-06-06 | Comment on e-mail to companies | All |  | C
A007 | 2018-05-31 | 2018-06-01 | Make first draft of a list with company contacts | Carolien Stroomer |  | C
A008 | 2018-05-31 | 2018-06-13 | Add possibly interested companies/contacts to list | All |  | IP
A009 | 2018-05-31 | 2018-06-13 | Investigate what big data education and research is already going on at the HAN | All |  | O
A010 | 2018-06-13 | 2018-06-27 | Rephrase the research question for external communication | Tanja Vermeulen |  | O
A011 | 2018-06-13 | 2018-06-27 | Provide a total of 4 - 5 data projects for Carolien's students | Jan Benders |  | O
A012 | 2018-06-13 | 2018-06-27 | Make proposal programme Meetup | All |  | O
A013 | 2018-06-13 | 2018-06-27 | Build logistics plan Meetup | Tanja Vermeulen |  | O
A014 | 2018-06-13 | 2018-06-27 | Plan a data aggregation tool (eg web scraping vacancies) | Witek ten Hove / Jeroen Veen |  | O
A015 | 2018-06-13 | 2018-06-27 | News crawler for website OGBigD - demand / supply | Witek ten Hove / Jeroen Veen |  | O
A016 | 2018-06-13 | 2018-09-05 | Gather info on data education within HAN | All |  | O
A017
A018
A019
A020
A021
A022
A023
A024
A025
A026
A027
Formulas:
Due date = [Initialization date]+14
Due date = [Initialization date]+7*12